## Sheet1
Dates go below - you can also boldface key milestones. Be sure to add Stakeholder Meeting #3 in last week of May (can be before or after Jun 2 class basic demo). Colors: Green = done, Yellow = almost done, Red = needs to be done
Task Decompose tasks as much as you can. Be sure to include frequent testing, system integrations, design tasks, etc. | Leader (Note: each student should be leading a major technical subcomponent on project) | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | June 2: DUE: In class basic demo of prototype | 2022-06-03 | 2022-06-04 | 2022-06-05 | June 6: DUE: FP Presentation | 2022-06-07 | June 8 DUE: FP Report
1. Task 1: After Stakeholder Meeting 2
1.1 Subtask 1: Mini Project Proposal
1.1.1 Schedule a Time | Vidya | bar: 2022-05-20
1.1.2 Finish Gantt Chart | Vidya, Sally, Kai | bar: 2022-05-21 to 2022-05-22
1.1.3 Determine materials to purchase | Sally | bar: 2022-05-21 to 2022-05-23
1.1.4 Narrow down features to include in robot | Vidya | bar: 2022-05-21 to 2022-05-23
1.1.5 Write mini project proposal | Vidya | bar: 2022-05-22 to 2022-05-23
1.2 Subtask 2: Begin Ideating
1.2.1 Wireframe and create mockups | Kai | bar: 2022-05-20 to 2022-05-24
1.2.2 Check chosen features with availability of materials | Kai | bar: 2022-05-24 to 2022-05-25
2 Task 2: Start Building Robot
2.1 Subtask 1: Work on robot
2.1.1 Design the circuit system of the robot | Kai | bar: 2022-05-24 to 2022-05-27
2.1.2 Design the parts of the robot with CAD | Kai | bar: 2022-05-24 to 2022-05-27
2.1.3 3D-print / Cut-out the parts with polystyrene | Kai | bar: 2022-05-26 to 2022-05-28
2.1.4 Build skeleton of robot
2.1.4.1 Add basic mobility to robot (Motors) | Kai, Sally | bar: 2022-05-27 to 2022-05-29
2.1.4.2 Add head nudges component (Tactile Sensor) | Kai, Sally | bar: 2022-05-27 to 2022-05-29
2.1.4.3 Add audio component (Speaker) | Kai, Sally | bar: 2022-05-27 to 2022-05-29
2.1.5 Add skeleton to stuffed animal | Kai, Sally | bar: 2022-05-28 to 2022-05-29
2.2 Subtask 2: Work on busy blanket component
1.2.1 Put together base of busy blanket | Vidya, Sally | bar: 2022-05-24 to 2022-05-25
1.2.2 Add textural elements | Vidya, Sally | bar: 2022-05-25 to 2022-05-26
3 Task 3: Stakeholder Meeting #3
3.1 Subtask 1: Before Meeting Tasks | bar: 2022-05-30 to 2022-06-01
3.1.1 Review "Stakeholder Meeting 3" handout | Sally | bar: 2022-05-31 to 2022-06-01
3.1.2 Prepare 3rd Meeting Checklist | Kai | bar: 2022-05-31 to 2022-06-01
3.1.3 Send Zoom Link and Google Calendar Invite | Vidya
3.1.4 Add all team members including Professor Riek and Sachi to calendar link | Vidya
3.1.5 Check and Test Zoom Meeting Settings
3.2 Subtask 2: During Meeting Tasks
3.2.1 Demonstrate functionality of robot | Kai
3.2.2 Explain any uncompleted components of robot | Vidya
3.2.3 Gather stakeholder feedback | Sally
3.3 Subtask 3: After Meeting Tasks
3.3.1 Determine group meeting time | Kai
3.3.2 Evaluate feedback | Vidya
3.3.3 Add feasible last-minute changes (if any) | Sally
3.3.4 Invite stakeholders to the demo / presentation day | Sally | bar: 2022-06-01
4 Task 4: Prepare Final Report and Presentation
4.1 Subtask 1: Final Presentation
4.1.1 Prepare slides | Vidya, Sally, Kai
4.1.2 Practice presentation run-through | Vidya, Sally, Kai
4.2 Subtask 2: Final Report
4.2.1 Write and proofread final report | Vidya, Sally, Kai
4.3.2 Comment and clean up all code | Vidya, Sally, Kai